## Sheet1
Travel+Hotel Booking-Functional Testing -System Test Plan
Section 1: Test Plan identifier
Release Name | Release 1-Pilot version
Release descriprion | Flight + Hotel booking for the customer
Release Date | 2025-08-29
Section 2: REVISION HISTORY
Version Number | Date of Change | Action |  |  | Author
1 |  | Creation of test plan |  |  | Ramya
Section 3: INTRODUCTION
The test team will follow a structured methodology during System as well as Acceptance testing that closely mirrors the approach followed during the other testing phases. A set of system test cases will be created from the requirements and UI specs, and reviewed for completeness and accuracy. Business rule test cases will also be created as part of system test cases. Prior to test execution an entrance Criteria and Readiness Review will be held to ensure the test environment is ready for use. Once determined and the environment is built, the on-site/off-shore test team will execute the system and regression test cases using JIRA and manual test case execution. Defects will be logged, corrected, and re-tested, and all testing activities will be reviewed and documented in status reports and a final test summary report.  Test execution will be reported and managed by the Travel test team Business analysts will perform the majority of acceptance testing, but may decide to include other business partners in the activity.
Section 4: Features to be tested (In scope)
1. Search form
2. Flight Results page
3. Hotel Results page
4. Basket Page
5. Enquiry Page
6. Thank you Page
7. Booking Page
8. Payment Gateway
9. Confirmation Page
Section 5: Out of scope/Features not to be tested
NA
Section 6: TEST APPROACH (How is these stories going to be tested? Is there any way to achieve test coverage efficiently?)
 In general, We are creating test cases based on below approach • Page Level Testing • Rule Based test cases • Happy path • Non Happy path
Section 7: TEST TYPES (Fill in the test types applicable for this work request.)
Test Type |  |  | Y/N | Comments
Functional Testing |  |  | Y
Performance Testing |  |  | Y
Usability Testing |  |  | Y
Smoke Testing |  |  | Y
Sanity Testing |  |  | Y
Exploratory testing |  |  | Y
Database Testing |  |  | Y
Section 8: Entry Criteria and Exit criteria
Exit Criteria
1 | System Testing (Application Test Exit)
1.1 | Verify if All the tests planned have been run
1.2 | No open blocker defects remain.
1.3 | Verify All high-priority and critical defects are fixed & retested.
1.4 | Verify if high risk areas are completely tested
1.5 | Verify if software development activities are completed withoin the timelines and Cost.
Section 9.Risk and ISSUES
NA
Section 10: REFERENCES
Document Name |  |  | Link
01-Test Plan or Master Test plan |  |  | https://nxdev.site.traveltek.net/search/flighthotel
02- RTM or TICM |  |  | RTM Template'!A1
03-Test scenario-Test case-Test script template |  |  | Test Scenarios'!A1
04-Sample Test data sheet or Address sheet
05-Test Results
06-Defect Report |  |  | Defect Report'!A1
07-Test Summary Report |  |  | Test Summery'!A1
08-Signoff document or Release notes
23- SRS document
24- High level design document
SIGN OFF/APPROVAL
BA
QA Offshore
QA Onshore