## Sheet1
Test Case Execution & Defects Summary:
Module | Total TC's | Executed | Passed | Failed | Blocked | Hold | Pending to Execute | Defect # | Remarks
Flight Search | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Flight Filter | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Hotel Search | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 1 | Defect found while selecting hotel
Hotel Filter | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
Enquiry | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Booking payment | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Total | 22 | 22 | 21 | 1 | 0 | 0 | 0 | 1
Percentage | 100% | 100 | 95.4545 | 4.5455 | 0 | 0 | 0
Defect Metrics
Module/Severity/Priority | Highest | High | Medium | Low | Total Open | Total Closed | Remarks
[5 empty] | Defects | Defects
Hotel Booking | 0 | 0 | 1 | 0 | 1 | 0 | Defect found in Select button functionality
Flight Booking | 0 | 0 | 0 | 0 | 0 | 0 | No defects found
Payment | 0 | 0 | 0 | 0 | 0 | 0 | No defects found
Total | 0 | 0 | 1 | 0 | 1 | 0